## START HERE
Project Charter Detail Timeline
1. Choose the tab in this worksheet that best represents your project type.
2. Delete all other tabs (leave this one and possibly the Import Instructrions if you want to be able to import your dates to your calendar
3. On the tab you have chosen, fill out the top section, making sure to put your Event Date in C3.
4. Save this document and submit it to the project charter.
The list of tasks you see are representative of your event type and the steps required for planning. It is a guideline but should give you an idea on rough timing. Some steps may not apply. Use this as a tool for planning.

## DistrictActivity
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
DACT - Meet with Program Chair to identify Event Chair | -160 | enter date in C3
DACT - Recruit Chairman, select committee | -140 | enter date in C3
DACT - Event Committee Meeting, Develop Budget and Program | -126 | enter date in C3
DACT - Event Committee promotes at Roundtable | -90 | enter date in C3
DACT - Event Committee Meeting Order patches, ribbons, supplies Mail information Facilities arranged | -84 | enter date in C3
DACT - Recruit Staff | -63 | enter date in C3
DACT - Event Committee promotes at Roundtable | -60 | enter date in C3
DACT - Promotion at Roundtable, email | -56 | enter date in C3
DACT - Event Committee Meeting Details completed Medical arrangements made | -42 | enter date in C3
DACT - Event Committee promotes at Roundtable | -30 | enter date in C3
DACT - Final program set | -14 | enter date in C3
DACT - Set Up | -14 | enter date in C3
DACT - Event | 0 | enter date in C3
DACT - Follow-up, Thank you, Budget final | 7 | enter date in C3

## DistrictCamporee
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
DCMP - Meet with Program Chair to identify Camporee Chairman | -170 | enter date in C3
DCMP - Recruit Chairman | -140 | enter date in C3
DCMP - Recruit Committee | -133 | enter date in C3
DCMP - Secure Location | -126 | enter date in C3
DCMP - Hold Committee Meeting | -126 | enter date in C3
DCMP - Promote with troops | -119 | enter date in C3
DCMP - Hold Committee Meeting, develop program | -91 | enter date in C3
DCMP - Develop recognition plan and patch | -91 | enter date in C3
DCMP - Physical facilities arranged | -91 | enter date in C3
DCMP - Have final budget approved by staff leader | -90 | enter date in C3
DCMP - Committee promotes Camporee at Roundtable | -90 | enter date in C3
DCMP - Mail Camporee Booklet | -60 | enter date in C3
DCMP - Submit Camporee Booklet in electronic format to webmaster to post | -60 | enter date in C3
DCMP - Committee promotes Camporee at Roundtable | -60 | enter date in C3
DCMP - Recuest PO and order patches | -56 | enter date in C3
DCMP - Arrange for religious observance | -49 | enter date in C3
DCMP - Recruit judging personnel | -49 | enter date in C3
DCMP - Lay out troop sites and plan assignments | -49 | enter date in C3
DCMP - Advance publicity | -42 | enter date in C3
DCMP - Committee promotes Camporee at Roundtable | -30 | enter date in C3
DCMP - Prepare Camporee signs | -28 | enter date in C3
DCMP - Develop Special Guest List, hold Committee meeting | -28 | enter date in C3
DCMP - Arrange for first aid and hospital emergency service | -21 | enter date in C3
DCMP - Arrange for HQ setup | -21 | enter date in C3
DCMP - Arrange facilities for Trading Post, PA System, etc., if needed | -14 | enter date in C3
DCMP - Complete details for final program bulletin; reproduce and mail | -14 | enter date in C3
DCMP - Plan evening program and assign responsibilities | -14 | enter date in C3
DCMP - Pick - up materials and take to site | -7 | enter date in C3
DCMP - Set- up | 0 | enter date in C3
DCMP - Hold Camporee | 0 | enter date in C3

## CubScoutDayCamp
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
DDC - Meet with Program Chairs to identify directors | -300 | enter date in C3
DDC - Select Day Camp Director and Program Director | -280 | enter date in C3
DDC - Camp School dates and forms to directors | -250 | enter date in C3
DDC - Day Camp Meeting - discuss program, dates, staff, budget, fees and camp school dates | -240 | enter date in C3
DDC - Meet with Directors to identify staff | -210 | enter date in C3
DDC - Select and Secure Site and date, send in material for promotion, secure transportation | -200 | enter date in C3
DDC - Deadline for site, date and director information to Council Office for production of Day Camp Brochure and Camp Promotion material | -189 | enter date in C3
DDC - Key Staff recruited | -150 | enter date in C3
DDC - Council Day Camp meeting - Review draft of brochure, t-shirt, patch design | -150 | enter date in C3
DDC - Camp Promotion Begins by Day Camp Staff at Roundtables, Blue and Gold Banquets, Individual Pack meetings | -145 | enter date in C3
DDC - Brochure to printer | -121 | enter date in C3
DDC - Director and Program Director to Council Day Camp Administration Meeting | -107 | enter date in C3
DDC - Train Key Staff, plan program themes, develop staff manual | -100 | enter date in C3
DDC - Brochures printed and mailed | -100 | enter date in C3
DDC - Follow up meeting with Council Day Camp Chair and directors | -90 | enter date in C3
DDC - Order craft and material items | -90 | enter date in C3
DDC - Staff meeting for planning of unit visitations and promotion | -90 | enter date in C3
DDC - Staff meeting, finalize manual | -60 | enter date in C3
DDC - Order patches | -56 | enter date in C3
DDC - Precamp Inspection | -30 | enter date in C3
DDC - T-shirt sizes and quantity; patch numbers to office | -30 | enter date in C3
DDC - Staff Training on site for den leaders and helpers; Parent's meeting | -7 | enter date in C3
DDC - Set Up | -1 | enter date in C3
DDC - Day Camp | 0 | enter date in C3
DDC - Camp Visitation | 1 | enter date in C3
DDC - Day Camp Review | 7 | enter date in C3
DDC - Director and Program Director to Council Day Camp Administration Meeting for final review and evaluation. Promotion pictures and overall theme to be determined. | 75 | enter date in C3

## DistrictProgramKickofff
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
DPPC - Secure location | -70 | enter date in C3
DPPC - Develop program with Key 4 | -70 | enter date in C3
DPPC - Promote at Roundtable and other district meetings | -70 | enter date in C3
DPPC - Submit final agenda for Program Preview Conference to supervisor and camp | -60 | enter date in C3
DPPC - Order supplies from office | -60 | enter date in C3
DPPC - Conference notice prepared and mailed | -35 | enter date in C3
DPPC - Program assignments reviewed with district operating committee chairman, finalize agenda and make assignments | -35 | enter date in C3
DPPC - Assemble all materials | -30 | enter date in C3
DPPC - Follow - up with program presenters | -14 | enter date in C3
DPPC - Telephone calls to unit leaders inviting them to event | -14 | enter date in C3
DPPC - Final check on facility | -7 | enter date in C3
DPPC - Setup and hold conference | 0 | enter date in C3
DPPC - Follow - up | 7 | enter date in C3

## DistrictDinner
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
DRB - Meet with Program Chair to identify top prospects to recruit | -184 | enter date in C3
DRB - Recruit Chairman | -154 | enter date in C3
DRB - Recruit Committee | -140 | enter date in C3
DRB - Hold committee meeting and confirm date time and place | -119 | enter date in C3
DRB - Develop budget | -119 | enter date in C3
DRB - Program developed | -119 | enter date in C3
DRB - Begin promotion of banquet | -119 | enter date in C3
DRB - Mail "Save the Date" postcard (electronic) | -91 | enter date in C3
DRB - Begin personal contacts | -49 | enter date in C3
DRB - Mail invitation | -45 | enter date in C3
DRB - Final check on physical arrangements | -42 | enter date in C3
DRB - Printed program booklet designed | -42 | enter date in C3
DRB - Order recognition items and ribbons | -42 | enter date in C3
DRB - Finalize agenda assignments | -35 | enter date in C3
DRB - Program finalized and printed | -14 | enter date in C3
DRB - Finalize detailed agenda and review with chairman | -14 | enter date in C3
DRB - Finalize meal plans and confirm final count | -7 | enter date in C3
DRB - Setup for dinner | 0 | enter date in C3
DRB - Hold dinner | 0 | enter date in C3
DRB - Follow - up thank you's | 7 | enter date in C3

## ScoutingForFood
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
SFF - Identify sponsor for event and volunteer to assist in recruitment | -180 | enter date in C3
SFF - Secure sponsor for event | -180 | enter date in C3
SFF - Identify top prospects for chair and volunteers to assist in recruitment | -180 | enter date in C3
SFF - District Committee identifies plans and prospects | -180 | enter date in C3
SFF - Secure Council Chairman for Scouting for Food | -150 | enter date in C3
SFF - District Scouting for Foods Chairs secured | -130 | enter date in C3
SFF - Invitations sent for Oreintation | -130 | enter date in C3
SFF - Arrangements made for Scouting for Food bags | -120 | enter date in C3
SFF - Arrangements made for Drop Off Locations | -120 | enter date in C3
SFF - Arrangements made for Delivery Trucks | -120 | enter date in C3
SFF - Orientation for all Chairs | -100 | enter date in C3
SFF - Communication with District personnel | -90 | enter date in C3
SFF - Order Patches | -60 | enter date in C3
SFF - Information to Unit Leaders through Roundtable and email | -60 | enter date in C3
SFF - Good Turn for America ID's available | -45 | enter date in C3
SFF - Bags and maps to Unit Leaders | -30 | enter date in C3
SFF - Bags placed by units | -7 | enter date in C3
SFF - Scouting for Food | 0 | enter date in C3
SFF - Follow up with units on submitting Good Turn for America | 7 | enter date in C3
SFF - Thanks you letters | 7 | enter date in C3
SFF - Follow up and Evaluation Meeting | 14 | enter date in C3

## TrainingCourse
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date
TRAN - Meet with Training Chair(s) to identify training course director | -150 | enter date in C3
TRAN - Recruit course director | -120 | enter date in C3
TRAN - Send pre-notice to unit leaders, asking for identification of leaders needing to be trained | -90 | enter date in C3
TRAN - Recruit and train counselors | -90 | enter date in C3
TRAN - Determine who is to be trained | -84 | enter date in C3
TRAN - Develop list of prospective course participants | -84 | enter date in C3
TRAN - Receive training need from unit leaders and turn into council office | -75 | enter date in C3
TRAN - Give Online Registration information to webmaster | -75 | enter date in C3
TRAN - Build mailing data base | -65 | enter date in C3
TRAN - Start promotion at Roundtables and council and district events by Training Event Staff | -60 | enter date in C3
TRAN - Mail notice | -60 | enter date in C3
TRAN - Chair and staff orientation: Review syllabus, make staff assignments | -60 | enter date in C3
TRAN - Online Registration begins | -45 | enter date in C3
TRAN - Arrange meeting place | -42 | enter date in C3
TRAN - Order supplies | -42 | enter date in C3
TRAN - Promote at district committee meeting | -30 | enter date in C3
TRAN - Begin personal contacts | -28 | enter date in C3
TRAN - Promote at roundtable | -28 | enter date in C3
TRAN - Review agenda and Syllabus with Course director | -21 | enter date in C3
TRAN - Check on arrangements, equipment and exhibits | -14 | enter date in C3
TRAN - Send reminder notice by email | -14 | enter date in C3
TRAN - Finalize personal contacts | -7 | enter date in C3
TRAN - Hold training session | 0 | enter date in C3
TRAN - Follow - up, thank - you letters and turn in training report | 7 | enter date in C3

## Template
PROJECT TASK DETAILS
Project Name
Project Start Date
Project Leader
Step to be completed | Days Before/ After | Event Date